8th Grade Career Fair Timeline

March/April

- Contact Athletic Director for gym availability in the month of October

- Check availability of other buildings that will be used

- Update contacts list

- Poll schools regarding available dates (email #0)

- Notify Athletic Director of selected date

- Reserve gym through VC Administrative Affairs Office & add to College calendar

- Begin enlisting volunteers (registration, tour guides, lunch, bus drop-off)

April/May

- Notify schools to save the date (email #1)

- Schedule first planning meeting and identify careers/programs

- Review programs and revise if needed – stress that all full-time CTE/HS faculty should plan to participate

- Possible Additions:

June/July

- Create rotation schedule

- Second planning meeting

- Begin collecting door prize giveaways

  - Send email to program leads with suggestions for door prizes (gift cards, etc.)

August

- Third planning meeting

- Confirm room locations for each program

- Notify security to leave doors unlocked

- Review previous years’ maps and determine if changes need to be made

- Email schools (first week of school) reminder about Career Fair and include registration information.

- Arrange IT setup (ITS), gym setup (maintenance) & photographer (marketing)

- Finalize registration form and test it

- Reserve vans/bus

- Enlist van drivers

- Reserve Leo the Lion Costume

Eight Weeks Prior

- Contact food service & lock in date

- Confirm presenters for each session

- Send empmail requesting volunteers for tour guides & Spanish speaking volunteers

- Launch website

- Send email announcing registration dates (email #3)

Six Weeks Prior

- Open registration

- Monitor registration

Four Weeks Prior

- Collect large boxes to store backpacks in

Three Weeks Prior

- Presenters notify IT if they need guest accounts or any special software or setup in the computer lab they will be using.

- Send email #4 (Registration reminder & chaperones)

- Send photo release form

- Close Registration

Two Weeks Prior

- Compile list of students registered and send to schools to review

- Make Corrections to students list

- Collect photo release forms

- Identify non-English speaking students

- Place students in cohorts

- Touch base with program leads.

- Print maps, schedules, etc. for tour guides

One Week Prior

- Send email #5 (check in with presenters)

- Print list of students for tour guides

- Stuff backpacks

- Send email #6 (Career Fair Details including Fact Sheet for ISD personnel)

- Print list of students for schools & tour guides

- Print list of tour guides with assignments and attendance check-off

Week of Career Fair

- Deliver backpacks to schools

- Send Email #7 (list of students)

- Include list of students that have registered and chaperone group assignments for each school

- Send Email #8 to presenters (final instructions)

Day of Career Fair

- Meet with tour guides and go over their route

- Distribute surveys to all rooms

- Check off names of tour guides

- Record number of students attending from each school

- Be sure to collect signs from tour guides

- Collect surveys

Week Following Career Fair

- Send thank you email to all presenters (Email #9)

- Send thank you email to ITS, Marketing & others that helped out

- Send thank you to industry partners

- Begin compiling survey results

Two to Three Weeks Following Career Fair

- Career Fair Follow-up meeting